Nguyễn Dương Phúc - 24521386

Exercise 1

A software company is building a new mobile app with a budget of $200,000.

- Planned Value (PV): $80,000

- Earned Value (EV): $60,000

- Actual Cost (AC): $75,000

Questions:

1. Calculate Cost Variance (CV) and CPI – Is the project (budget) on track?

2. Compute Schedule Variance (SV) and SPI – Is the project (schedule) on track?

3. Find TCPI – Can the project recover?

Giải

Given

BAC = 200,000

PV = 80,000

EV = 60,000

AC = 75,000

1.1

CV = EV - AC = 60,000 - 75,000 = -15,000

CV < 0: Over Budget

CPI = EV / AC = 60,000 / 75,000 = 0.8

CPI < 1: Over Budget

- The project (budget) is not on track

1.2

SV = EV - PV = 60,000 - 80,000 = -20,000

SV < 0: Behind Schedule

SPI = EV / PV = 60,000 / 80,000 = 0.75

SPI < 1: Delayed

- The project (schedule) is not on track

1.3

TCPI = (BAC - EV) / (BAC - AC) = (200,000 - 60,000) / (200,000 - 75,000) = 1.12

TCPI > 1: tough recovery

Exercise 2

Given the following project information for a 1-year project:

- Planned Value (PV) = $23,000

- Earned Value (EV) = $20,000

- Actual Cost (AC) = $25,000

- Budget at Completion (BAC) = $120,000

Questions:

1. Calculate Cost Variance (CV) and CPI. Is the project over budget?

2. Calculate Schedule Variance (SV) and SPI. Will the project be completed behind or ahead of schedule?

3. Recalculate the new budget (EAC) for this project.

4. Reestimate how long it will take (ETC) to complete the project.

Giải

Given

PV = 23,000

EV = 20,000

AC = 25,000

BAC = 120,000

TAC = 1 year

2.1

CV = EV - AC = 20,000 - 25,000 = -5,000
CV < 0: Over budget

CPI = EV / AC = 20,000 / 25,000 = 0.8

CPI < 1: Over Budget

- The project is over budget

2.2

SV = EV – PV = 20,000 - 23,000 = -3,000

SV < 0: Behind Schedule

SPI = EV / PV = 20,000 / 23,000 = 0.87

SPI < 1: Delayed

- The project will be completed behind schedule

2.3

EAC (budget) = BAC / CPI = 120,000 / 0.8 = 150,000

2.4

EAC (time) = TAC / SPI = 1 / 0.87 = 1.15 (years)

ETC (time) = EAC (time) – Current time 
*đề chưa cho current time